## Sheet1
Summary Milestones | Due Date
All industrial and government permits obtained | 2014-12-20
All design and engineering plans documents are ready | 2015-01-05
All contracts awarded & facility construction begins on site | 2015-02-25
Facility construction ends | 2015-04-28
Equipment installation ends and testing starts | 2015-05-10
Final approvals and hand over to the client | 2015-05-20