## Project Charter

Project Title: Biomass Energy Project

Project Sponsor: CoGP (City of Grand Prairie)	Date Prepared: 2014-04-15

Project Manager: Mr. Jose Mourinho		Project Customer: ELC (Eastlink) Recreation Centre

Project Purpose or Justification:

- Promoting use of clean energy by undertaking Biomass energy project

- Gain credit from Government under different programs

- Capacity expansion by various industry sectors

- Incremental demand for commercial space by tapping into the market where feedstock is disposed as scrap

- Increase use of renewable  capacity to supply the national demand for various  industries and its products

- Increase the production capacity to use the opportunity to cleaner and greener environment

Project Description:

The objective of this project involves replacing one of the older used propane boilers with a new 400 kW wood pellet boiler. The new boiler supplies 80-85% of the heat demand for the entire ERC.

Secondly, the project is to modify the infrastructure of the building to combine the heating systems of two buildings to layout the common piping and to facilitate the heat supply to both the buildings from the single boiler.

Project and Product Requirements:

Acceptance Criteria:

Initial Risks:

|  | Project Objectives | Success Criteria | Person Approving |
| --- | --- | --- | --- |
| Scope | To manage scope without adding unnecessary requirements to the project | Delivering fully operational cement plant satisfying client requirements | Project manager and project sponsor/customer |
| Time | To complete the project on time. Time~~ 4 months 15 days | Implementing the project on time considering allocated 10% contingency | Project manager |
| Cost | To stay under budget and incur as few incidental expenditures as possible | Implementing the project within budget considering 10% contingency | Project manager |
|  | Budget ~~ $1.28 million |  |  |
| Quality | Conform to project requirements with high quality deliverables | Completing the project without permit violations and getting final operating license | Canadian Standards Association (CSA) |

| Summary Milestones | Due Date |
| --- | --- |
| All industrial and government permits obtained | 20/12/2014 |
| All design and engineering plans documents are ready | 05/01/2015 |
| All contracts awarded & facility construction begins on site | 25/02/2015 |
| Facility construction ends | 28/04/2015 |
| Equipment installation ends and testing starts | 10/05/2015 |
| Final approvals and hand over to the client | 20/05/2015 |

Estimated Budget:

Project Manager Authority Level Staffing Decisions:

Budget Management and Variance:

Technical Decisions:

Conflict Resolution:

Escalation Path for Authority Limitations:

Approvals:

Project Manager Signature	                                        	Sponsor / Originator Signature

JOSE MOURINHO	                                 SKP Projects

Project Manager Name	                                                 	Sponsor / Originator Name

Date	                                                                                           Date

# Text boxes

Schedule: Meet or beat established project milestones considering allocated contingencies

Budget: Implementing the project within budget considering allocated contingencies

Scope: Conform to project requirements without adverse effects on milestones or budget

Safety: No recordable injuries more than the industry average

Legal compliance: Complete project without permit violations

Quality: passing the final inspection test according to Boiler standards

- Fire and explosion which may occur because of using flammable liquids for engine combustion, plastics and combustible materials, welding works, heaters in warehouses, transformers for electricity supply, and compressors

- Catastrophic risks such as winds, storms, hurricanes and cyclones, ground subsidence, landslides and rock falls

- Defects  in  workmanship  such  as  carelessness  in  handling  equipment  which  may  cause innumerable damages to the own work as well as to third parties

- Errors in calculation or design and employment of defective or inadequate material

- Accidents in plant site that may result in insufficient labour resources

This project is estimated to require $ 1.28 million budget with 10% contingency. This estimation is obtained based on previously done similar project and meetings with subject matter experts.

The project manager will have the authority to release or bring in any necessary resources to contribute to the project team.

The project manager has authority to make decisions about controlling and allocating the project budget pending approval from the project sponsor.

The project manager has the authority to make technical decisions about the project. However, all technical decisions will be made in advisement with the subject matter experts on the project.

The project manager will be expected to negotiate between stakeholders and resolve any conflicts that may arise during the project.

Any items or issues that are not resolved by the project manager or project team will be taken to the director level. If not resolved there, the issue will flow to the executive level.