## Introduction
Managing risk for Recreational Facilities Biomass project
What is risk management?
Risk management is a process of identifying and then actively managing risk for projects with the aim of making the project more likely to succeed.
Risk management should:
· Improve delivery certainty
· Concentrate minds and actions on the big issues
· Put the organisation in control with a measurable process
· Enable better, informed, decisions
· Provide a meaningful link between contingency and risk
· Improve communication and understanding
Key risks for low carbon buildings
The top 5 perceived risks and risk response strategies are:
Risk description | Risk response strategy
Planning permission delays or permission not granted for wind turbines | Early discussions with Planners and on-going discussions with Case Officers
Over optimistic costs used at feasibility stage | Upfront involvement of experienced contractor
Incorrect technology chosen at feasibility stage | Rigorous feasibility study including use of performance benchmarks
Planning permission delays or permission not granted for photovoltaic panels | Early discussions with Planners and on-going discussions with Case Officers
Environment Agency extraction licence for open loop ground source and renewal may not be granted | Seek permission from Environment Agency as part of early feasibility study
Go to Risk Register

## Risk Register
Total Risks | 11
Open | 11
Red | 3
Orange | 6
Amber | 1
Green | 1
Data Check | Data Valid
Risk Rating Total | 37620
Ave Risk Rating | 3420 | Ramp
Less Than 1 | #REF! | 1000
1-3 | #REF! | 500
3-6 | #REF! | 50
6-12 | #REF! | 5
More than 12 | #REF! | 1
[33 empty] | MC Output: | CLT Outputs:
Risk Identification | [5 empty] | Current Assessment | [9 empty] | Risk Management | [7 empty] | Target Assessment | [7 empty] | Risk Quantification (14a-14f MC) (14g-14h CLT)
1 | 1a | 1b | 2 | 3 | 3a | 4 | 5 | 4b | 4c | 4d | 4e |  | 5a | 6 | 7 | 8 | 9 | 9a | 9b | 10 | 11 | 12 | 13 | 13a | 13b | 13c | 13d |  |  | 13e | 13f | 14a | 14b | 14c | 14d | 14e | 14f | 14g | 14h
No | Risk Owner | Threat, Opp or Issue | Risk Description | Consequence | Category | Likelihood | Sustainability | Time Impact | Fit for Purpose | Health&Safety | Reputation | Max | Risk Matrix | Rating | Risk Status | Risk Response Strategy | Management Actions Taken | Management Actions Planned | NEC Owner | Action Owner | Date By | Last Updated | Comments | Likelihood | Cost Impact | Time Impact | Quality Impact | Max | Rating | Rating | Risk Status | Probability (e.g. 0.9) | Occurred This Iteration? | Minimum £ (000's) | Most Likely £ (000's) | Maximum £ (000's) | Value from Iteration £ (000's) | Expected Value | Variance
1 |  | Threat | Planning Approvals Planning permission delays or permission not granted for boiler change Causes 1. Community complaints 2. Adjacency to residential areas 3. Failure to comply Planning legislation guidance 4. Perceived risk of not obtaining planning permission | 1. Not able to implement technology of choice 2. Potential delays to the programme 3. Potential cost overruns | Approvals | 3 | 5 |  |  |  |  | 5 | 35 | 8000 | RED | Early discussions with Planners and on-going discussions with Case Officers |  | 1. On larger/ complex projects appoint a Planning Consultant. 2. Pro-active discussions with the Planners. |  |  |  |  | Higher risk on smaller projects. |  |  |  |  | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
2 |  | Threat | Costs Exceeded Over optimistic costs used at feasibility stage Causes 1. Costs based on assumptions and hence not comprehensive | 1. Potential cost overruns | Financial | 3 | 5 |  |  |  |  | 5 | 35 | 8000 | RED | Upfront involvement of experienced contractor |  | 1. Appoint experienced Cost Consultant in renewable advice 2.Ensure costs are comprehensive, including installation, supports, controls etc. 3. Consider Whole Life Costs approach | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
3 |  | Threat | Incorrect Technology Incorrect technology chosen at feasibility stage Causes 1. Decisions based on visual and or PR considerations rather than financial 2. Poor feasibility study/ advice | 1. Performance reduction compared to expectations | Technology | 4 | 4 |  |  |  |  | 4 | 44 | 6000 | RED | Rigorous feasibility study including use of performance benchmarks |  | 1. Carbon Trust to advise on best case 2. Appoint a Carbon advisor 3. Consider a Whole Life costings approach to demonstrate value 4. Desk study and tests to demonstrate feasibility of the proposal i.e. wind monitoring or boreholes at an early stage 5. Better due diligence on supplier 6. Appropriate choice of technology to match maintenance capability 7. Reduce complexity 8. Skilling up operational staff | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
4 |  | Threat | Planning Approvals Planning permission delays or permission not granted for photovoltaic panels Causes 1. Listed building issues 2. Complaints based on aesthetics | 1. Not able to implement technology of choice 2. Potential delays to the programme 3. Potential cost overruns | Approvals | 2 | 5 |  |  |  |  | 5 | 25 | 4000 | ORANGE | Early discussions with Planners and on-going discussions with Case Officers |  | 1. Comply with National and Local Authority guidance |  |  |  |  | L.A barriers should be minimal with a growing positivity towards this initiative |  |  |  |  | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
5 |  | Threat | Environment Agency Approval Environment Agency extraction licence for open loop ground source and renewal may not be granted Causes 1. Current ground conditions | 1. Not able to implement technology of choice 2. Potential cost overruns | Approvals | 3 | 4 |  |  |  |  | 4 | 34 | 4000 | ORANGE | Seek permission from Environment Agency as part of early feasibility study |  | 1. Understand EA requirements | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
6 |  | Threat | Technology Conflicting technologies chosen at feasibility stage Causes 1. Decisions based on visual and or PR considerations rather than financial 2. Poor feasibility study/ advice 3. Chasing low carbon reduction targets | 1. Performance reduction compared to expectations | Technology | 3 | 4 |  |  |  |  | 4 | 34 | 4000 | Orange | Rigorous feasibility study including use of performance benchmarks |  | 1. Carbon Trust to advise on best case 2. Appoint a Carbon advisor 3. Consider a Whole Life costings approach to demonstrate value 4. Desk study and tests to demonstrate feasibility of the proposal i.e. wind monitoring or boreholes at an early stage 5. Better due diligence on supplier 6. Appropriate choice of technology to match maintenance capability 7. Reduce complexity 8. Skilling up operational staff 9. Undertake peer review of feasibility study |  |  |  |  | The key challenge is the integration of solar thermal with the DHW system for optimal performance of the solar thermal and the system. |  |  |  |  | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
7 |  | Threat | Planning Approvals Planning permission delays or permission not granted for biomass boilers Causes 1. Air quality issues 2. Transport deliveries 3. Perceived reluctance by some Local Authorities to give automatic approvals | 1. Not able to implement technology of choice 2. Potential delays to the programme 3. Potential cost overruns | Approvals | 2 | 4 |  |  |  |  | 4 | 24 | 2000 | ORANGE | Early discussions with planners and on-going discussions with the case officer. |  | 1. Carry out air quality assessment to demonstrate whether air quality is affected by proposals. | [13 empty] | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
8 |  | Threat | Natural ventilation Natural ventilation not providing sufficient cooling/ventilation Causes 1. Incorrect assumptions 2. Buildings are used differently than anticipated 3. Late changes to the design/ layouts | 1. Internal thermal comfort conditions not achieved | Design | 4 | 3 |  |  |  |  | 3 | 43 | 600 | ORANGE |  |  | 1. Pro-active discussions with the building occupiers 2. Extensive and ongoing modelling of internal conditions 3. Protect and ensure the Natural Ventilation Strategy is clear, understood by all parties and not diluted/ changed as the design progresses | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
9 |  | Threat | Equipment Availability Plant/equipment only available from a few specialist suppliers Causes 1. Low demand 2. High costs in manufacturing components | 1. Potential high costs of equipment 2. Lack of availability or long lead-in time | Training | 4 | 3 |  |  |  |  | 3 | 43 | 600 | ORANGE |  |  | 1. Aim to use more standard technologies where possible 2. Plan for long lead-in time | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
10 |  | Threat | Ground source heat pumps insufficient Open loop ground source heat pumps not delivering sufficient heating or cooling Causes 1. Pilot drill not undertaken 2. Decision based on surrounding buildings | 1. Potential failure to meet energy demands of building 2. Performance reduction compared to expectations | Delivery | 3 | 3 |  |  |  |  | 3 | 33 | 400 | AMBER |  |  | 1. Accurate energy modelling/calculations 2. Early performance testing (i.e. open loop boreholes) 3. Analyse the output of other local boreholes | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
11 |  | Threat | Technology Familiarity Design and Build contractors being unfamiliar with biomass energy technologies | 1. Potential cost increase | Contractual | 2 | 2 |  |  |  |  | 2 | 22 | 20 | GREEN |  |  | 1. Ensure contractors are vetted correctly | [9 empty] | 0 | 0 | #N/A | #N/A | #REF! | #NAME? | 0 | 0 | 0 | #NAME? | #REF! | #REF!
Note on Z26: Neil Briefly: Updated from 1 to 2 - NB/ID - 10.1.08
Note on AC34: Neil Briefly: No value included - rating of 1 added by NB/ID - 10.1.08
Note on AC35: Neil Briefly: No value included - rating of 1 added by NB/ID - 10.1.08
Note on AC30: Neil Briefly: No rating included - 1 added - NB/ID 10.1.08
Note on AC31: Neil Briefly: No rating included - 1 added - NB/ID 10.1.08
Back to introduction

## ROAG Base Data (hidden)
ROAG Status
Likelihood | Rating | Impact | Rating | Code | Rating (L*I) | Brag Status
1 | 2 | 1 | 1 | 11 | 2 | GREEN
1 | 2 | 2 | 5 | 12 | 10 | GREEN
1 | 2 | 3 | 50 | 13 | 100 | AMBER
1 | 2 | 4 | 500 | 14 | 1000 | ORANGE
1 | 2 | 5 | 1000 | 15 | 2000 | ORANGE
2 | 4 | 1 | 1 | 21 | 4 | GREEN
2 | 4 | 2 | 5 | 22 | 20 | GREEN
2 | 4 | 3 | 50 | 23 | 200 | AMBER | Likelihood |  | Impact
2 | 4 | 4 | 500 | 24 | 2000 | ORANGE | VL | 2 | VL | 1
2 | 4 | 5 | 1000 | 25 | 4000 | ORANGE | L | 4 | L | 5
3 | 8 | 1 | 1 | 31 | 8 | GREEN | M | 8 | M | 50
3 | 8 | 2 | 5 | 32 | 40 | AMBER | H | 12 | H | 500
3 | 8 | 3 | 50 | 33 | 400 | AMBER | VH | 16 | VH | 1000
3 | 8 | 4 | 500 | 34 | 4000 | ORANGE
3 | 8 | 5 | 1000 | 35 | 8000 | RED | The likelihood and impact ranges can be changed in the boxes above to suit the project.
4 | 12 | 1 | 1 | 41 | 12 | GREEN
4 | 12 | 2 | 5 | 42 | 60 | AMBER
4 | 12 | 3 | 50 | 43 | 600 | ORANGE
4 | 12 | 4 | 500 | 44 | 6000 | RED
4 | 12 | 5 | 1000 | 45 | 12000 | RED
5 | 16 | 1 | 1 | 51 | 16 | GREEN
5 | 16 | 2 | 5 | 52 | 80 | AMBER
5 | 16 | 3 | 50 | 53 | 800 | ORANGE
5 | 16 | 4 | 500 | 54 | 8000 | RED
5 | 16 | 5 | 1000 | 55 | 16000 | RED

## L & I Ranges (hidden)
LIKELIHOOD AND IMPACT RANGES
LIKELIHOOD
| Description | Scenario | Code Letter | Guide Probability | RAMP Value
| Very High | Almost certain to occur | VH | 90 | 16
| High | More likely to occur than not | H | 75 | 12
| Medium | Fairly likely to happen | M | 50 | 8
| Low | Low but not impossible | L | 25 | 4
| Very Low | Extremely unlikely to happen | VL | 5 | 2
IMPACT
| Description | Scenario | Code Letter | RAMP Value | Guide Cost % of Project | Guide Time % of Prog.
| Very High | Critical impact on the achievement of objectives and overall performance. Huge impact on costs and/or reputation. Very difficult and possibly long-term to recover. | VH | 1000 | 2 | 5
| High | Major impact on costs, objectives. Serious impact on output and/or quality and reputation. Medium to long-term effect and expensive to recover. | H | 500 | 1.5 | 3
| Medium | Reduces viability significant waste of time and resources and impact on operational efficiency, output, and quality. Medium term effect, which may be expensive to recover. | M | 50 | 1 | 1.5
| Low | Minor loss, delay, inconvenience or interruption. Short to medium term effect. | L | 5 | 0.5 | 0.75
| Very Low | Minimal loss, delay, inconvenience or interruption. Can be easily and quickly remedied. | VL | 1 | 0.25 | 0.25