## Sheet1
Project Name: Green Biomass Project |  | Project Manager: Jose Mourinho
Project Sponsor: SKP Projects |  | Status Date |  | 2014-12-02
Project Status:
Project Start: November 1, 2014 |  | Project End |  | 2014-12-18 | Project Days Remaining: | 16
Tasks: | Completion Dates |  | Task Days Remaining | Risk | Achievements
| (double click on cell for calendar) |  |  |  | Created WBS and WBS Dictionary on time
| Baseline | Actual
Charts & supporting documents:
Stakeholder Register | 2014-11-24 | 2014-12-01 | 7 | low
WBS + WBS Dictionary | 2014-11-24 | 2014-11-24 | 0 | low | Issues
Milestone list | 2014-11-24 | 2014-12-01 | 7 | med | Finalizing the resources and budget compression
Project schedule | 2014-11-24 | 2014-12-02 | 8 | low
Risk Register | 2014-12-01 | 2014-12-02 | 1 | low
Project management plan: |  |  |  |  | Risks
Scope baseline | 2014-11-24 | 2014-12-01 | 7 | low | Budget and Project Schedule over run
Schedule baseline | 2014-11-24 | 2014-12-01 | 7 | low
Cost baseline | 2014-11-24 | 2014-12-03 | 9 | med
Scope management plan | 2014-11-24 | 2014-12-01 | 7 | low
Requirements management plan | 2014-12-04 | 2014-12-08 | 4 | low | Key Decisions & Change Requests
Schedule management plan | 2014-12-04 | 2014-12-08 | 4 | low
Cost management plan | 2014-12-04 | 2014-12-08 | 4 | low
Quality management plan | 2014-12-04 | 2014-12-08 | 4 | low
Process improvement plan | 2014-12-04 | 2014-12-08 | 4 | med
Human resource management plan | 2014-12-14 | 2014-12-14 | 0 | med | Next Steps
Communications management plan | 2014-12-14 | 2014-12-14 | 0 | med | Project Schedule Plan and other management plan completion stepwise
Risk management plan | 2014-12-14 | 2014-12-14 | 0 | high
Procurement management plan | 2014-12-14 | 2014-12-14 | 0 | high
Stakeholder management plan | 2014-12-14 | 2014-12-14 | 0 | med

## validation
select:
high
med
low