## Stakeholder Register
Name | Position | Role | Communication Requirements | Project Expectations | Classification | Influence
City of Grand Prairie (CoGP),Alberta Government | Project sponsor | Provide funding and approvals | Monthly meeting, Weekly telephone and email updates | Project delivery based on requirements | Internal | Positive
Jose Mourinho | Project manager | Drive overall project direction and plans to effectively complete deliverables | Emails, face-to-face meetings, weekly regular meetings, phone, progress reports, status reports | Collaboration from everyone in the project team | Internal | Positive
Project Team | Planner/ Scheduler | Support project manager through project control processes | Weekly meetings, status reports, presentations, progress reports | Motivation from the project manager | Internal | Positive
Mechanical Engineer
Electrical Engineer
Instrumentation Engineer
Operation & Process Engineer
HSEF Engineer
Civil & Structural Engineer
Mechancal Maintenance Team
Electrical Maintenance Team
Instrumentation Maintenance Team
Lionel Messi | Procurement/ Contracting Engineer | Representative of the purchasing and contracts department | Bi-weekly meetings, status reports, presentations | Precise design requirements documents from the project team | Internal | Positive
Durable relations with subcontractors and suppliers
Contractor Companies & Suppliers | Contractor Companies & Suppliers | Continued collaboration and interest in providing more material services to the company | Meetings, emails, phone | Timely orders | External | Positive
Invoices paid according to negotiated terms
People and residents of City of CoGP | Local Communities | Participation in the stakeholder consultation process | Advertising | New job opportunities | External | Neutral
Repair and improvement of roads quality
Reduced vehicle traffic and dust generation as a result of the use of an enclosed belt conveyor instead of heavy trucks for limestone transportation
Government authorities & other regulatory bodies | Government authorities & other regulatory bodies | Participation in the process of project approval and issuing of necessary permits | Quarterly email updates , end of project report | Tax payments to the city and municipal budgets | External | Neutral
New job creation
Compliance with government and municipal legislation
Legend:
Classification | Influence
Internal | Positive
External | Neutral
Negative